## Activities
Component | Activity | Duration | Resource Requirement | Predecessors
1 | 1 | 4 | 19
1 | 2 | 9 | 13 | 1
1 | 3 | 5 | 8 | 1
1 | 4 | 5 | 28 | 1, 2, 3
1 | 5 | 1 | 15 | 1, 2, 3
2 | 6 | 3 | 11
2 | 7 | 7 | 17 | 6
2 | 8 | 2 | 15
2 | 9 | 5 | 17 | 6
2 | 10 | 9 | 29 | 6, 8, 9
3 | 11 | 1 | 15
3 | 12 | 3 | 8
3 | 13 | 8 | 10 | 11
3 | 14 | 7 | 9
3 | 15 | 9 | 5 | 12
4 | 16 | 112 | 10
4 | 17 | 34 | 5
4 | 18 | 60 | 5 | 16
4 | 19 | 108 | 10 | 16, 17
4 | 20 | 78 | 19 | 18, 19
5 | 21 | 40 | 16
5 | 22 | 182 | 19 | 21
5 | 23 | 62 | 4 | 21
5 | 24 | 10 | 5 | 22
5 | 25 | 40 | 6 | 21, 23, 24
6 | 26 | 46 | 19
6 | 27 | 90 | 13 | 26
6 | 28 | 164 | 19 | 27
6 | 29 | 168 | 10 | 26, 27, 28
6 | 30 | 38 | 5 | 27
7 | 31 | 48 | 15
7 | 32 | 14 | 5 | 31
7 | 33 | 34 | 5 | 31
7 | 34 | 64 | 15 | 31, 32
7 | 35 | 16 | 14 | 31, 33, 34
8 | 36 | 162 | 12
8 | 37 | 50 | 7
8 | 38 | 178 | 19 | 36, 37
8 | 39 | 60 | 4 | 36, 37
8 | 40 | 70 | 5 | 38, 39
9 | 41 | 10 | 19
9 | 42 | 8 | 17
9 | 43 | 9 | 28 | 41
9 | 44 | 3 | 23 | 41, 42
9 | 45 | 9 | 28 | 42
10 | 46 | 8 | 26
10 | 47 | 6 | 27 | 46
10 | 48 | 3 | 18 | 47
10 | 49 | 9 | 25
10 | 50 | 9 | 28 | 48

## Component_Sets
J_prime_fixed_S1 | J_postponable | J2_required | J_intersection_J2 | J_not_in_J2 | J2_not_in_J
1 | 4 | 6 | 6 | 4 | 9
2 | 5 | 9 |  | 5 | 10
3 | 6 | 10 |  | 7
| 7 |  |  | 8
8

## Parameters
Parameter | Value
Duration_S1 | 400
Duration_S2 | 468
Start_time_S1 | 1
End_time_S1 | 400
Start_time_S2 | 500
End_time_S2 | 968
Resource_availability_S1 | 46
Resource_availability_S2 | 79
Budget_S1 | 18400
Budget_S2 | 73944
Cost_per_resource_S1 | 1
Cost_per_resource_S2 | 2
Number_of_scenarios | 32
Total_activities | 50

## Failure_Cost_Data
Component | Failure_probability_alpha | Maintaining_probability_beta | Corrective_maintenance_cost | Expected_corrective_cost
4 | 0.61 | 0.3 | 19513 | 11902.93
5 | 0.5 | 0.14 | 28725 | 14362.5
6 | 0.43 | 0.11 | 13181 | 5667.83
7 | 0.43 | 0.21 | 24395 | 10489.85
8 | 0.48 | 0.17 | 16790 | 8059.2

## Activities_by_Component
Component | Activities
1 | [1, 2, 3, 4, 5]
2 | [6, 7, 8, 9, 10]
3 | [11, 12, 13, 14, 15]
4 | [16, 17, 18, 19, 20]
5 | [21, 22, 23, 24, 25]
6 | [26, 27, 28, 29, 30]
7 | [31, 32, 33, 34, 35]
8 | [36, 37, 38, 39, 40]
9 | [41, 42, 43, 44, 45]
10 | [46, 47, 48, 49, 50]

## Activity_Parameters
Activity | Duration | Resource_requirement
1 | 4 | 19
2 | 9 | 13
3 | 5 | 8
4 | 5 | 28
5 | 1 | 15
6 | 3 | 11
7 | 7 | 17
8 | 2 | 15
9 | 5 | 17
10 | 9 | 29
11 | 1 | 15
12 | 3 | 8
13 | 8 | 10
14 | 7 | 9
15 | 9 | 5
16 | 112 | 10
17 | 34 | 5
18 | 60 | 5
19 | 108 | 10
20 | 78 | 19
21 | 40 | 16
22 | 182 | 19
23 | 62 | 4
24 | 10 | 5
25 | 40 | 6
26 | 46 | 19
27 | 90 | 13
28 | 164 | 19
29 | 168 | 10
30 | 38 | 5
31 | 48 | 15
32 | 14 | 5
33 | 34 | 5
34 | 64 | 15
35 | 16 | 14
36 | 162 | 12
37 | 50 | 7
38 | 178 | 19
39 | 60 | 4
40 | 70 | 5
41 | 10 | 19
42 | 8 | 17
43 | 9 | 28
44 | 3 | 23
45 | 9 | 28
46 | 8 | 26
47 | 6 | 27
48 | 3 | 18
49 | 9 | 25
50 | 9 | 28

## Precedence
Successor | Predecessor
2 | 1
3 | 1
4 | 1
4 | 2
4 | 1
4 | 3
4 | 1
4 | 1
5 | 2
5 | 1
5 | 3
5 | 1
5 | 1
7 | 6
9 | 6
10 | 6
10 | 6
10 | 8
10 | 6
10 | 9
13 | 11
15 | 12
18 | 16
19 | 17
19 | 16
20 | 18
20 | 19
20 | 18
20 | 19
22 | 21
23 | 21
24 | 22
25 | 23
25 | 21
25 | 24
27 | 26
28 | 27
29 | 26
29 | 28
29 | 27
30 | 27
32 | 31
32 | 31
33 | 31
33 | 31
34 | 31
34 | 32
35 | 31
35 | 34
35 | 33
35 | 34
38 | 36
38 | 37
39 | 37
39 | 36
40 | 38
40 | 39
43 | 41
44 | 41
44 | 42
45 | 42
47 | 46
48 | 47
50 | 48

## Scenarios
Scenario_number | Component_4 | Component_5 | Component_6 | Component_7 | Component_8
1 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 1
3 | 0 | 0 | 0 | 1 | 0
4 | 0 | 0 | 0 | 1 | 1
5 | 0 | 0 | 1 | 0 | 0
6 | 0 | 0 | 1 | 0 | 1
7 | 0 | 0 | 1 | 1 | 0
8 | 0 | 0 | 1 | 1 | 1
9 | 0 | 1 | 0 | 0 | 0
10 | 0 | 1 | 0 | 0 | 1
11 | 0 | 1 | 0 | 1 | 0
12 | 0 | 1 | 0 | 1 | 1
13 | 0 | 1 | 1 | 0 | 0
14 | 0 | 1 | 1 | 0 | 1
15 | 0 | 1 | 1 | 1 | 0
16 | 0 | 1 | 1 | 1 | 1
17 | 1 | 0 | 0 | 0 | 0
18 | 1 | 0 | 0 | 0 | 1
19 | 1 | 0 | 0 | 1 | 0
20 | 1 | 0 | 0 | 1 | 1
21 | 1 | 0 | 1 | 0 | 0
22 | 1 | 0 | 1 | 0 | 1
23 | 1 | 0 | 1 | 1 | 0
24 | 1 | 0 | 1 | 1 | 1
25 | 1 | 1 | 0 | 0 | 0
26 | 1 | 1 | 0 | 0 | 1
27 | 1 | 1 | 0 | 1 | 0
28 | 1 | 1 | 0 | 1 | 1
29 | 1 | 1 | 1 | 0 | 0
30 | 1 | 1 | 1 | 0 | 1
31 | 1 | 1 | 1 | 1 | 0
32 | 1 | 1 | 1 | 1 | 1