## Activities
Component | Activity | Duration | Resource Requirement | Predecessors
1 | 1 | 3 | 18
1 | 2 | 2 | 6
1 | 3 | 9 | 7
1 | 4 | 3 | 10 | 1, 2, 3
1 | 5 | 7 | 4 | 2, 3
2 | 6 | 6 | 21
2 | 7 | 10 | 8
2 | 8 | 10 | 3
2 | 9 | 4 | 17 | 6, 7
2 | 10 | 3 | 10 | 6, 7, 8, 9
3 | 11 | 6 | 3
3 | 12 | 10 | 9
3 | 13 | 6 | 16
3 | 14 | 3 | 7
3 | 15 | 9 | 7 | 12
4 | 16 | 84 | 7
4 | 17 | 34 | 7 | 16
4 | 18 | 96 | 8 | 16
4 | 19 | 34 | 10 | 17, 18
4 | 20 | 14 | 6 | 19
5 | 21 | 24 | 4
5 | 22 | 20 | 6
5 | 23 | 74 | 7
5 | 24 | 158 | 8 | 21, 22, 23
5 | 25 | 34 | 7 | 21, 22, 23
6 | 26 | 56 | 7
6 | 27 | 24 | 7 | 26
6 | 28 | 24 | 6
6 | 29 | 160 | 7 | 28
6 | 30 | 100 | 10 | 28, 29
7 | 31 | 126 | 7
7 | 32 | 196 | 8 | 31
7 | 33 | 100 | 11 | 31, 32
7 | 34 | 160 | 7 | 33
7 | 35 | 64 | 4 | 33
8 | 36 | 46 | 8
8 | 37 | 56 | 5 | 36
8 | 38 | 40 | 4 | 36
8 | 39 | 54 | 2 | 36
8 | 40 | 44 | 4 | 37, 38
9 | 41 | 8 | 19
9 | 42 | 6 | 18
9 | 43 | 2 | 21
9 | 44 | 4 | 20
9 | 45 | 8 | 14
10 | 46 | 6 | 22
10 | 47 | 9 | 18
10 | 48 | 7 | 27
10 | 49 | 2 | 11
10 | 50 | 5 | 22 | 46
11 | 51 | 3 | 9
11 | 52 | 2 | 10
11 | 53 | 4 | 23
11 | 54 | 2 | 17 | 51, 53
11 | 55 | 1 | 8 | 51, 52, 53

## Component_Sets
J_prime_fixed_S1 | J_postponable | J2_required | J_intersection_J2 | J_not_in_J2 | J2_not_in_J
1 | 4 | 4 | 4 | 5 | 9
2 | 5 | 7 | 7 | 6 | 10
3 | 6 | 9 |  | 8 | 11
| 7 | 10
| 8 | 11

## Parameters
Parameter | Value
Duration_S1 | 522
Duration_S2 | 582
Start_time_S1 | 1
End_time_S1 | 522
Start_time_S2 | 622
End_time_S2 | 1204
Resource_availability_S1 | 33
Resource_availability_S2 | 92
Budget_S1 | 17226
Budget_S2 | 107088
Cost_per_resource_S1 | 1
Cost_per_resource_S2 | 2
Number_of_scenarios | 32
Total_activities | 55

## Failure_Cost_Data
Component | Failure_probability_alpha | Maintaining_probability_beta | Corrective_maintenance_cost | Expected_corrective_cost
4 | 0.64 | 0.23 | 13259 | 8485.76
5 | 0.5 | 0.13 | 16028 | 8014
6 | 0.53 | 0.19 | 26276 | 13926.28
7 | 0.42 | 0.23 | 10992 | 4616.64
8 | 0.46 | 0.17 | 18670 | 8588.2

## Activities_by_Component
Component | Activities
1 | [1, 2, 3, 4, 5]
2 | [6, 7, 8, 9, 10]
3 | [11, 12, 13, 14, 15]
4 | [16, 17, 18, 19, 20]
5 | [21, 22, 23, 24, 25]
6 | [26, 27, 28, 29, 30]
7 | [31, 32, 33, 34, 35]
8 | [36, 37, 38, 39, 40]
9 | [41, 42, 43, 44, 45]
10 | [46, 47, 48, 49, 50]
11 | [51, 52, 53, 54, 55]

## Activity_Parameters
Activity | Duration | Resource_requirement
1 | 3 | 18
2 | 2 | 6
3 | 9 | 7
4 | 3 | 10
5 | 7 | 4
6 | 6 | 21
7 | 10 | 8
8 | 10 | 3
9 | 4 | 17
10 | 3 | 10
11 | 6 | 3
12 | 10 | 9
13 | 6 | 16
14 | 3 | 7
15 | 9 | 7
16 | 84 | 7
17 | 34 | 7
18 | 96 | 8
19 | 34 | 10
20 | 14 | 6
21 | 24 | 4
22 | 20 | 6
23 | 74 | 7
24 | 158 | 8
25 | 34 | 7
26 | 56 | 7
27 | 24 | 7
28 | 24 | 6
29 | 160 | 7
30 | 100 | 10
31 | 126 | 7
32 | 196 | 8
33 | 100 | 11
34 | 160 | 7
35 | 64 | 4
36 | 46 | 8
37 | 56 | 5
38 | 40 | 4
39 | 54 | 2
40 | 44 | 4
41 | 8 | 19
42 | 6 | 18
43 | 2 | 21
44 | 4 | 20
45 | 8 | 14
46 | 6 | 22
47 | 9 | 18
48 | 7 | 27
49 | 2 | 11
50 | 5 | 22
51 | 3 | 9
52 | 2 | 10
53 | 4 | 23
54 | 2 | 17
55 | 1 | 8

## Precedence
Successor | Predecessor
4 | 3
4 | 2
4 | 1
5 | 2
5 | 3
9 | 7
9 | 6
10 | 8
10 | 6
10 | 7
10 | 6
10 | 9
15 | 12
17 | 16
18 | 16
19 | 17
19 | 18
20 | 19
24 | 21
24 | 22
24 | 23
25 | 21
25 | 22
25 | 23
27 | 26
29 | 28
30 | 29
30 | 28
32 | 31
33 | 32
33 | 31
34 | 33
35 | 33
37 | 36
38 | 36
39 | 36
40 | 37
40 | 38
50 | 46
54 | 51
54 | 53
55 | 51
55 | 52
55 | 53

## Scenarios
Scenario_number | Component_4 | Component_5 | Component_6 | Component_7 | Component_8
1 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 1
3 | 0 | 0 | 0 | 1 | 0
4 | 0 | 0 | 0 | 1 | 1
5 | 0 | 0 | 1 | 0 | 0
6 | 0 | 0 | 1 | 0 | 1
7 | 0 | 0 | 1 | 1 | 0
8 | 0 | 0 | 1 | 1 | 1
9 | 0 | 1 | 0 | 0 | 0
10 | 0 | 1 | 0 | 0 | 1
11 | 0 | 1 | 0 | 1 | 0
12 | 0 | 1 | 0 | 1 | 1
13 | 0 | 1 | 1 | 0 | 0
14 | 0 | 1 | 1 | 0 | 1
15 | 0 | 1 | 1 | 1 | 0
16 | 0 | 1 | 1 | 1 | 1
17 | 1 | 0 | 0 | 0 | 0
18 | 1 | 0 | 0 | 0 | 1
19 | 1 | 0 | 0 | 1 | 0
20 | 1 | 0 | 0 | 1 | 1
21 | 1 | 0 | 1 | 0 | 0
22 | 1 | 0 | 1 | 0 | 1
23 | 1 | 0 | 1 | 1 | 0
24 | 1 | 0 | 1 | 1 | 1
25 | 1 | 1 | 0 | 0 | 0
26 | 1 | 1 | 0 | 0 | 1
27 | 1 | 1 | 0 | 1 | 0
28 | 1 | 1 | 0 | 1 | 1
29 | 1 | 1 | 1 | 0 | 0
30 | 1 | 1 | 1 | 0 | 1
31 | 1 | 1 | 1 | 1 | 0
32 | 1 | 1 | 1 | 1 | 1